## Test Scenarios
SNO# | Req# ID | Scenarios | No of test cases
1 | 3,1,1 | ESS user Login | 4
2 | 3,1,1 | ESS user can view Personal details | 1
3 | 3,1,1 | ESS user can edit Personal details | 1
4 | 3,1,1 | ESS user can not edit restricted fields in Personal details | 1
5 | 3,1,2 | ESS user can add a fotograph | 12
6 | 3,1,3 | ESS user can view Contact details | 1
7 | 3,1,3 | ESS user can edit Contact details | 1
8 | 3,1,4 | ESS user can add Emergency contact | 1
9 | 3,1,4 | ESS user can add multiple Emergency contact | 1
10 | 3,1,4 | ESS user can delete Emergency contact | 1
11 | 3,1,5 | ESS user can add Dependant | 1
12 | 3,1,5 | ESS user can add multiple Dependant | 1
13 | 3,1,5 | ESS user can delete Dependant | 1
14 | 3,1,6 | ESS user can add immegration details | 1
15 | 3,1,6 | ESS user can add multiple entrees of immigration | 1
16 | 3,1,6 | ESS user can delete immigration details | 1
17 | 3,1,6 | ESS user can attach documents under immigration Records | 1
18 | 3,1,7 | ESS user can not change job details | 1
19 | 3,1,8 | ESS user restricted from editing Salary components | 1
20 | 3,1,9 | ESS user can only view the list of supervisors | 1
21 | 3,1,10 | ESS user can add working experience | 1
22 | 3,1,10 | ESS user can add multiple work experience | 1
23 | 3,1,10 | ESS user can delete working experience | 1
24 | 3,1,10, | ESS user can add education | 1
25 | 3,1,10 | ESS user can add multiple entrees of education | 1
26 | 3,1,10 | ESS user can delete education | 1
27 | 3,1,10 | ESS user can add skills | 1
28 | 3,1,10, | ESS user can add multiple entrees of skills | 1
29 | 3,1,10 | ESS user can delete skills | 1
30 | 3,1,10 | ESS user can add languages | 1
31 | 3,1,10 | ESS user can add multiple languages | 1
32 | 3,1,10 | ESS user can delete languages | 1
33 | 3,1,10, | ESS user can add licenses | 1
34 | 3,1,10 | ESS user can add multiple licenses | 1
35 | 3,1,10 | ESS user can delete licenses | 1
36 | 3,1,10 | ESS user can add attachments regarding qualification | 1
37 | 3,1,11 | ESS user can add a membership | 1
38 | 3,1,11 | ESS user can add multiple entrees of memberships | 1
39 | 3,1,11 | ESS user can delete a membership | 1

## Test Cases(Exec. report)
TC#ID | Project/Module name | Req#ID | Scenario | Test Case Title | Steps | Test Data | Expectations | Actual results | Status(Passed/Failed)
TC_My_Info_001 | Orange HRM_My_Info | 3,1,1 | ESS user login | Verify login with valid ESS username and valid password | 1) Launch browser 2)Open URL "https://opensource-demo.orangehrmlive.com" 3)Provide valid ESS username 4)Provide valid password 5)Click on log-in button | John1234/John1234 | Login succersfull. ESS user should seem successfull. | Dashboard is displayed after login is successfull instead of MyInfo page | Failed(P3)
TC_My_Info_002 | Orange HRM_My_Info | 3,1,1 | ESS user login | Verify login with valid ESS username and in-valid password | 1) Launch browser 2)Open URL "https://opensource-demo.orangehrmlive.com" 3)Provide valid ESS username 4)Provide in-valid password 5)Click on log-in button | John1234/zxasd | invalid credentials | As expected | Passed
TC_My_Info_003 | Orange HRM_My_Info | 3,1,1 | ESS user login | Verify login with in-valid ESS username and valid password | 1) Launch browser 2)Open URL "https://opensource-demo.orangehrmlive.com" 3)Provide in-valid ESS username 4)Provide valid password 5)Click on log-in button | zxasd/John1234 | invalid credentials | As expected | Passed
TC_My_Info_004 | Orange HRM_My_Info | 3,1,1 | ESS user login | Verify login with in-valid ESS username and in-valid password | 1) Launch browser 2)Open URL "https://opensource-demo.orangehrmlive.com" 3)Provide in-valid ESS username 4)Provide in-valid password 5)Click on log-in button | zxcvasd/ asdfgfa | invalid credentials | As expected | Passed
TC_My_Info_005 | Orange HRM_My_Info | 3,1,1 | ESS user can view Personal details | Verify ESS user is able to view Personal details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on Personal details link | N/A | User should be able to view personal details | As expected | Passed
TC_My_Info_006 | Orange HRM_My_Info | 3,1,1 | ESS user can edit Personal details | Verify ESS user can edit some fields in Personal details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on Personal details link 4) Click on Edit button 5)Edit full name, middle name, last name, license experience date, gernder, martial status and nationality. | N/A | User should be able to edit and save details | As expected | Passed
TC_My_Info_007 | Orange HRM_My_Info | 3,1,1 | ESS user can not edit restricted fields in Personal details | Verify ESS user can not edit restricted fields | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on Personal details link 4) Click on Edit button | N/A | The folowing fields should be non editable Employee ID SSN No SIN No Driver License Number Date of birth | As expected (Clarification Required on SSN number (Not visible on MyInfo->personal details link) | Partially Passed
TC_My_Info_008 | Orange HRM_My_Info | 3,1,2 | ESS user can add a photograph | Verify ESS user can add a photograph | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on the photograph on the corner of the screen 4) Click browse and select a photograth from the relevant path 5) click upload once you have selected the picture | images Size <= 1mb file format - jpg, png, gif, exe-fail | An error should be displayed that it is an invalid file format when you upload non supported files(like exe.) | The massage of invalid file type should appear (as only jpg, png, gif files are supported) after the upload button. But it uploads the complete exe file and than gives a massage that the file tipe is not supported. | Failed(P2).
TC_My_Info_009 | Orange HRM_My_Info | 3,1,3 | ESS user can view contact details | Verify ESS user is able to view contact details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on Contact details link | N/A | User should be able to view contact details | As expected | Passed
TC_My_Info_010 | Orange HRM_My_Info | 3,1,3 | ESS user can edit contact details | Verify ESS user can edit some fields in contact details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on Contact details link 4)Click on Edit button 5)Edit fields Adress street1, Adress street2, City state, Country, Zip Code, Phone, Email 6) Click on save button. | N/A | User should be able to edit and save contact details | As expected | Passed
TC_My_Info_011 | Orange HRM_My_Info | 3,1,4 | ESS user can add Emergency contact | Verify ESS user can add Emergency contact | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3) Click on Emergency Contacts link 4) Click on Add button 5) Provide Emergency Contact details -Name(mandatory) -Relationship(mandatory) -Home telephone -Mobile telephone 6) Click on Save button | N/A | Succesfully saved. Details should appear under Emergency Contacts table | As expected | Passed
TC_My_Info_012 | Orange HRM_My_Info | 3,1,4 | ESS user can add multiple Emergency contact | Verify ESS user can add multiple Emergency contacts | Repeat steps from TC_My_Info_011 | N/A | Succesfully saved. Multiple Emergency Contact details should appear under Emergency Contacts table | As expected | Passed
TC_My_Info_013 | Orange HRM_My_Info | 3,1,4 | ESS user can delete Emergency contact | Verify ESS user can delete Emergency contacts | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3) Click on Emergency Contacts link 4) Click on the check box next to particular entree 5) Click on delete button | N/A | Successfully Deleted. Entries should dissapear from Emergency Contacts table. | As expected | Passed
TC_My_Info_014 | Orange HRM_My_Info | 3,1,5 | ESS user can add Dependant | Verify ESS user can add Dependant | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3) Click on Depandants link 4) Click on Add button under Assigned dependants 5) Provide details -Name(mandatory) -Relationship(mandatory) -Date of birth -Mobile telephone 6) Click on Save button | N/A | Succesfully Saved. Dependant details should appeare under Assigned Dependants table. | As expected | Passed
TC_My_Info_015 | Orange HRM_My_Info | 3,1,5 | ESS user can add multiple Dependant | Verify ESS user able to add Dependant | Repeat steps from TC_My_Info_014 | N/A | Succesfully saved. Multiple dependants details should be appeared under assigned dependants table. | As expected | Passed
TC_My_Info_016 | Orange HRM_My_Info | 3,1,5 | ESS user can delete Dependant | Verify ESS user able to delete Dependant | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3) Click on Depandants link 4) Click on the check box next to particular entree 5) Click on delete button | N/A | Succesfully deleted. Entrees should disapear from Assigned Dependants table. | As expected | Passed
TC_My_Info_017 | Orange HRM_My_Info | 3,1,6 | ESS can add immigration details | Verify ESS user is able to add immigration details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Select on immigration Under Personal details 4) Click add, click on passport or visa, provide details -Number, issuad date, expire date, Eligable status, issued by, Comments. 5) Click on save button | N/A | Succesfully saved. Immigration details should be appeared under assigned immigration records. | As expected | Passed
TC_My_Info_018 | Orange HRM_My_Info | 3,1,6 | ESS can add multiple entrees of immigration | Verify ESS user is able to add multiple immigration details | Repeat steps from TC_My_info_017 | N/A | Succesfully saved. Multiple immigration details should be appeared under assigned immigration records. | As expected | Passed
TC_My_Info_019 | Orange HRM_My_Info | 3,1,6 | ESS user can delete Immigration | Verify ESS user is able to delete immigration details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Select on immigration Under Personal details. 4) Click on the check box next to particular entree 5) Click on delete button | N/A | Succesfully deleted. Entrees should disapear from Assigned imigration records table. | As expected | Passed
TC_My_Info_020 | Orange HRM_My_Info | 3,1,6 | ESS user can attach documents under immigration records | Verify ESS user is able to attach documents. | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Select on immigration Under Personal 4)at bottom of screen Click "add" and then select a attachments from the relevant path. 5) Click "Upload" once you have selected the file. | images | Succesfully saved attachment . Details should appear under imigration table. | As expected | Passed
TC_My_Info_021 | Orange HRM_My_Info | 3,1,7 | ESS user can not change job details | Verift ESS user can not change job details | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on job details link 4) Click on edit button. | N/A | The folowing fields should be non editable- Job specification Employment Status Job category Joined date Sub unit Location Employment contract start date | As expected | Passed
TC_My_Info_022 | Orange HRM_My_Info | 3,1,8 | ESS user restricted from editing salary components. | Verify ESS user restricted from editing salary components. | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on salary details. 4) Click on edit button. | N/A | The folowing fields should be non editable - Salary component Pay frequency Currency Amount Comments Direct deposit details Attachment | As expected | Passed
TC_My_Info_023 | Orange HRM_My_Info | 3,1,9 | ESS user can only view the list of supervisors | Verify ESS user can view the list of supervisors | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on report to | N/A | The ESS employee should be able to view assighned supervisor | As expected | Passed
TC_My_Info_024 | Orange HRM_My_Info | 3,1,10 | ESS user can add working experience | Verify ESS user can add working experience | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add working experience" 5) Provide the following information -Name of the company (mandatory) -Job title (mandatory) -Start date -End date -Comments | N/A | Succesfuly saved. Details should appear under work experience table. | As expected | Passed
TC_My_Info_025 | Orange HRM_My_Info | 3,1,10 | ESS user can add multiple work experience | Verify ESS user is able to add multiple working experience | Repeat steps from TC_My_Info_024 | N/A | Succesfuly saved. Multiple work experience details should appear under work experience table. | As expected | Passed
TC_My_Info_026 | Orange HRM_My_Info | 3,1,10 | ESS user can delete work experience | Verify ESS user is able to delete work experience. | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4)Click on the check box next to work experience you want to delete. 5) Click delete. | N/A | Successfully deleted. Work Experience should disappear from the qualifications table. | As expected | Passed
TC_My_Info_027 | Orange HRM_My_Info | 3,1,10 | ESS user can add education | Verify ESS user can add education. | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add Education" 5) Provide the following information -Level of education (mandatory) -Institute -Major / Specialisation -Year -GPA/ Score -Start date -End date | N/A | Successfully added. Education details should appear under Education table | As Expected(Only PostGraduation level of education is available(No Bachelor's degree or PhD degree available). Need clarification on Institute, specialization, GPA scor, end data. Not visible on MyInfo ->Qualifications link. Start / End date should not be more than current date. GPA/ Score must be a number not a letter | Partially Passed(P2)
TC_My_Info_028 | Orange HRM_My_Info | 3,1,10 | ESS user can add multiple entrees of educations | Verify ESS user can add multiple educations. | Repeat steps from TC_My_Info_027 | N/A | Successfully added. Multiple education details appear under Education table. | As Espected. | Passed
TC_My_Info_029 | Orange HRM_My_Info | 3,1,10 | ESS user can delete education | Verify ESS user can delete education. | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on check box next to Education ESS user need to delete. 5) Click delete | N/A | Successfully deleted. Education should disapear from the Education table. | As Expected | Passed
TC_My_Info_030 | Orange HRM_My_Info | 3,1,10 | ESS user can add skills | Verify ESS user is able to add skills | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add Skills" 5) Provide the following information -Skills (mandatory) -Years of experience -Comments if necessary | N/A | Successfully added. Skills details should appear under Qualifications->Skills table. | As expected(Only Guidwire skill is availabe, no other skills). | Partially Passed(P2)
TC_My_Info_031 | Orange HRM_My_Info | 3,1,10 | ESS user can add multiple entrees of skills | Verify ESS user is able to add multiple entrees of skills | Repeat steps from TC_My_Info_030 | N/A | Successfully added. Multiple skills details should appear under Qualifications->Skills table. | Only Guidwire skill is availabe, no other skills. | Failed(P1)
TC_My_Info_032 | Orange HRM_My_Info | 3,1,10 | ESS user can delete skills | Verify ESS user can delete skills | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on check box next to Skills ESS user need to delete. 5) Click delete | N/A | Successfully deleted. Skills should dissapear from the Skills table. | As expected. | Passed
TC_My_Info_033 | Orange HRM_My_Info | 3,1,10 | ESS user can add languages | Verify ESS user is able add languages | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add Languages" 5) Provide the following information -Language (mandatory) -Fluency (mandatory) -Competency (mandatory) -Comments . | N/A | Successfully added. Language details should appear under Qualifications ->Languages table. | No languages available. Can not add languages | Failed(P1)
TC_My_Info_034 | Orange HRM_My_Info | 3,1,10 | ESS user can add multiple entrees of languages | Verify ESS user is able to add multiple entrees of languages | Repeat steps from TC_My_Info_033 | N/A | Successfully added. Multiple language details should appear under Qualifications ->Languages table. | No languages available. Can not add Multiple languages | Failed(P1)
TC_My_Info_035 | Orange HRM_My_Info | 3,1,10 | ESS user can delete languages | Verify ESS user can delete languages | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" ->Languages 4) Click on check box next to languages ESS user need to delete. 5) Click delete | N/A | Successfully deleted. Languages should dissapear from the Languages table. | No languages available. Can not delete languages | Failed(P1)
TC_My_Info_036 | Orange HRM_My_Info | 3,1,10 | ESS user can add licenses | Verify ESS user is able to add licenses | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add License" 5) Provide the following information -License type (mandatory) -License number -Isuue date -Expire date | N/A | Successfully added. License details should appear under Qualifications -> License table. | As expected (Only one License type is available, License Number, Issue date and expire date are not mandatory). | Parialy passed(P2)
TC_My_Info_037 | Orange HRM_My_Info | 3,1,10 | ESS user can add multiple entrees of licenses | Verify ESS user is able to add multiple entrees of licenses | Repeat steps from TC_My_Info_036 | N/A | Successfully added.Multiple license details should appear under Qualifications -> License table. | No more License types can be added | Failed(P1)
TC_My_Info_038 | Orange HRM_My_Info | 3,1,10 | ESS user can delete license | Verify ESS user can delete license | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" ->Licenses 4) Click on check box next to languages ESS user need to delete. 5) Click delete | N/A | Successfully deleted. License details should dissapear from the Licenses table. | As expexted | Passed
TC_My_Info_039 | Orange HRM_My_Info | 3,1,11 | ESS user can add a membership | Verify ESS user is able to add a membership | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Memberships" and "Add" 4) Provide following information - Membership -Subscription paid by -Subscription Amount -Currency -Subscription Commence date -Subscription Renewal date | N/A | Successfully added. Membership details should appear under "Memberships" table | No memberships availablen, can not add membership | Failed(P1)
TC_My_Info_040 | Orange HRM_My_Info | 3,1,11 | ESS user can add multiple memberships | Verify ESS user can add multiple memberships | Repeat steps from TC_My_Info_039 | N/A | Successfully added. Multiple membership details should appear under "Memberships" table | No memberships availablen, can not add membership | Failed(P1)
TC_My_Info_041 | Orange HRM_My_Info | 3,1,11 | ESS user can delete a membership | Verify ESS user can delete a membership | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Memberships" 4) Click on check box next to membership ESS user need to delete. 5) Click delete | N/A | Successfully deleted.Memberships should dissapear from the Memberships table. | No Memberships can be deleted | Failed(P1)

## RTM
Test Execution Bug Reporting ------------------- Test execution ---------------------- 1)Test cases (Reviewd and Approved) 2)Build from Dev team(Integrated package) 3)Deploy the build on QA environment 4) Release Notes along with build -What is the new functionality implemented -What are the fixes available -Installation /Deployment steps | Test Phases: 1)Smoke and Sanity testing a)testing Build Installation(S1 (high severity)- Critical/Showstoupper/Blocker) b)Basic functionality is working or not(TAT(Tester acceptance test), BVT(build verification test), Shakedown test) -Page displayed or not -login is working or not -all the elements are displayed or not 2) Functional testing (Multiple cycles) -Progression testing (first time testing) -Regression testing (after fixing bugs second testing) -Retesting | 1)Execution Report(is the same as test cases only we have to update the last string). 2)Bug report | Pre-requisite: I need to login as Admin account and then create ESS user account. (URRL:https://opensource-demo.orangehrmlive.com). John1234 // John1234 | Sigh-off -------------------------------- Management team conducts a review meeting along with the team. -------------------------------- Discussing the folowing itams 1) All test cases executed and passed 2) All bugs have closed 3) There is no P0, P1, P2 bugs. --------------------------- Handover the final Bild/certified Bilt to UAT team.

## Bug Report
QA | [10 empty] | DEV
Bug ID | Module Name | Build # | Description | TCID | Steps to replicate bugs | Screenshot | Severity | Priority | Reported by | Assighned to | Resolution | Status | Fixed Date
ORHRM_001 | Orange HRM-MyInfo | 1 | Dashboard is displayed after login is successful instead of My Page | TC_MyInfo_001 | 1) Launch browser 2)Open URL "https://opensource-demo.orangehrmlive.com" 3)Provide valid ESS username 4)Provide valid password 5)Click on log-in button |  | S2 | P2 | John | Jack | Accepted | In progress
ORHRM_002 | Orange HRM-MyInfo | 1 | The invalid file format error massage for invalid photographs is appearing after the upload is completed. | TC_MyInfo_008 | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on the photograph on the corner of the screen 4) Click browse and select a photograth from the relevant path 5) click upload once you have selected the picture |  | S2 | P2 | John | Jack | Accepted | Open
ORHRM_003 | Orange HRM-MyInfo | 1 | When need to add Education, only PostGraduation level of education is available(No Bachelor's degree or PhD degree available). Need clarification on Institute, specialization, GPA scor, end data. Not visible on MyInfo ->Qualifications link. Start / End date should not be more than current date. GPA/ Score must be a number not a letter | TC_My_Info_027 | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add Education" 5) Provide the following information -Level of education (mandatory) -Institute -Major / Specialisation -Year -GPA/ Score -Start date -End date |  | S2 | P2 | John | Jack | Accepted | Open
ORHRM_004 | Orange HRM-MyInfo | 1 | Only one skill is available, no other skills (multiple skills) can be added | TC_My_Info_031 | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add Skills" 5) Provide the following information -Skills (mandatory) -Years of experience -Comments if necessary |  | S1 | P1 | John | Jack | Accepted | Open
ORHRM_005 | Orange HRM-MyInfo | 1 | There are no languages available language selection bar | TC_My_Info_033 | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add Languages" 5) Provide the following information -Language (mandatory) -Fluency (mandatory) -Competency (mandatory) -Comments . |  | S1 | P1 | John | Jack | Accepted | Open
ORHRM_006 | Orange HRM-MyInfo | 1 | Only one License type can be added. No more types are avaiable | TC_My_Info_037 | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Qualifications" 4) Click on "Add License" 5) Provide the following information -License type (mandatory) -License number -Isuue date -Expire date |  | S2 | P2 | John | Jack | Accepted | Open
ORHRM_007 | Orange HRM-MyInfo | 1 | No Memberships available, No Memberships can be added | TC_My_Info_039 | 1) Log-in to OrangeHRM as ESS user 2) Click on Myinfo tab 3)Click on "Memberships" and "Add" 4) Provide following information - Membership -Subscription paid by -Subscription Amount -Currency -Subscription Commence date -Subscription Renewal date |  | S1 | P1 | John | Jack | Accepted | Open